## Decision
BEFORE GO-LIVE IMPLEMENTATION READINESS
Independent fictional case - Felipe Mattos
Decision | NO-GO
Blocking actions | 10
Review items | 3
Employee records | 10
Enrollment records | 9
Status | Formal sign-off still required
Next | Correct source files, collect approvals, and revalidate

## Action Register
Area | Code | Priority | Owner | Required next action
Data integrity | INACTIVE_ENROLLMENT | BLOCKER | Employer HR | Check status and coverage eligibility
Data integrity | MISSING_START_DATE | BLOCKER | Employer HR | Supply verified employment start date
Data integrity | DUPLICATE_EMPLOYEE | BLOCKER | Employer HR | Confirm authoritative employee ID
Data integrity | PROVINCE_MISMATCH | BLOCKER | Carrier Relations | Validate provincial plan mapping
Data integrity | UNKNOWN_PLAN | BLOCKER | Carrier Relations | Verify plan identifier
Data integrity | UNKNOWN_EMPLOYEE | BLOCKER | Employer HR | Reconcile employee with authorized roster
Data integrity | DEPENDENTS_NOT_CONFIRMED | REVIEW | Client implementation | Confirm dependent information securely
Data integrity | MISSING_ENROLLMENT | REVIEW | Client implementation | Confirm waived coverage or missing form
Implementation gates | GATE_SIGNED_AUTHORIZATION | BLOCKER | Client HR | Confirm signed authorization with evidence
Implementation gates | GATE_CARRIER_FORMS_READY | BLOCKER | Carrier Relations | Confirm carrier forms ready with evidence
Implementation gates | GATE_CLIENT_VALIDATION | BLOCKER | Client HR | Confirm client validation with evidence
Carrier handoff | CARRIER_DEMO-CARRIER-B | BLOCKER | Carrier Relations | Obtain acknowledgement from DEMO-CARRIER-B
HRIS mapping | MAP_STATE | REVIEW | Systems / Implementation | Validate HRIS mapping state

## Client Gates
Gate | Status | Sample evidence
Kickoff scope | Complete | DEMO-KICK-001
Signed authorization | Pending
Effective date approved | Complete | DEMO-DATE-001
Carrier forms ready | Pending
Platform mapping review | Complete | DEMO-MAP-001
Client validation | Pending

## Carrier Handoff
Carrier reference | Acknowledgement | Evidence
DEMO-CARRIER-A | Confirmed | DEMO-ACK-001
DEMO-CARRIER-B | Pending

## HRIS Mapping
System | Source field | Sample destination | Verification
BambooHR | id | employee_id | Verified
BambooHR | hireDate | first_hire_date | Verified
BambooHR | status | status | Verified
BambooHR | state | residential_province | Needs review
BambooHR | terminationDate | termination_date | Verified

## Instructions
READ FIRST
All data, carriers and rules in this workbook are fictional.
This static workbook does not recalculate readiness when statuses are edited.
Update authoritative source CSVs and re-run the Python audit.
Passing checks is not proof of coverage, carrier acknowledgement or approved launch.